## Slide 1: Software Engineering
Dr. Owais Hussain

## Slide 2: Agenda
4Ps of Software Engineering
4PTRB Framework
W5HH Framework
Estimation: Lines of Code Analysis
Estimation: Function Point Analysis
This Photo by Unknown Author is licensed under CC BY

## Slide 3: Sample 2
4Ps of Software Engineering
People: the most important pillar, involving HR and effective team management.
Product: the software system to be built.
Process: the framework of activities and SE workflows to execute the project.
Project: planning, budgeting, timeline and resource allocation to develop the product.
Software development succeeds when right People use correct Process to build the required Product, while effectively managing the constraints and resources of the Project.

## Slide 4: Sample 2
4PTRB Software Project Management Framework
People
Communication
Teamwork
Process
Requirements Management
Project
Technology
Risk
Business
Leadership
Organizational Commitment
Stakeholder Involvement
Project Planning
Scope Management
Project Monitoring
Product
Quality Engineering
Configuration
Activity Definition
Activity Sequencing
Activity Resource Estimation
Scheduling
Cost Estimation
Budgeting
Technology Maturation
Risk Reduction
Knowledge Management
Risk Assessment
Risk Control
Contract Management
Procurement
Benefit Management

## Slide 5: Sample 2
W5HH Framework
The W5HH is a highly simplified concept that asks:
  WHAT will be the work to be done?
  WHY is the system being developed?
  WHEN will the system be ready for use?
  WHO are responsible for developing, verifying and managing it?
  WHERE are the stakeholders located?
  HOW will the work get done managerially and technically?
  HOW MUCH of each available resource is required?

## Slide 6: Sample 2
W5HH Framework
When answering these questions:
  WHAT is answered by the SRS.
  WHY is answered by Feasibility Report.
  WHEN is answered by Gantt Chart.
  WHO is answered by the SRS
  WHERE doesn’t matter in most cases nowadays.
  HOW is determined by the Process Model.
  HOW MUCH is determined through estimation processes.

## Slide 7: Sample 2
Estimation: Lines of Code Analysis
Lines of Code (LoC)
  Counting the number of statements in code.
  Comment and empty lines are excluded.
  Imports, variable declarations, and executable and non-executable statements are all included.
The output changes based on language; each coder’s output is a different estimate; can determine the size of code at best.
Notes: LoC is the most primitive metric and should not be used for real projects.

## Slide 8: Sample 2
Estimation: Lines of Code Analysis
/**
* Authenticates a user using email and password.
*
* @param email User's registered email address
* @param password Plain-text password entered by the user
* @return String Session token if login is successful
* @throws AuthenticationException if credentials are invalid or account is inactive
*/
public String loginUser(String email, String password) throws AuthenticationException {
if (email == null || password == null || email.isEmpty() || password.isEmpty())
throw new AuthenticationException("Email and password must not be empty");
User user = userRepository.findByEmail(email);
if (user == null)
throw new AuthenticationException("Invalid credentials");
if (!user.isActive())
throw new AuthenticationException("Account is not active");
boolean passwordMatch = passwordEncoder.matches(password, user.getPasswordHash());
if (!passwordMatch)
throw new AuthenticationException("Invalid credentials");
String sessionToken = sessionService.generateToken(user.getId());
return sessionToken;
}
Notes: This example shows how basic the LoC metric is. The Exceptions could have been merged into one to lower the estimate, the sessionToken assignment is not needed. What about logging? What about extra validations? What about calling other library functions?

## Slide 9: Sample 2
Estimation: Function Point Analysis
The Lines of Code Analysis can only be performed AFTER the code is written.
It can only estimate the size of a project.
There are several loopholes which may allow developers to produce larger code needlessly.
Function Point Analysis is a Standardized method to estimate complexity, size and functionality of a system.
FPA can work with prototype code as well (no implementation required).
It does not count lines of code but assesses what the software user does.

## Slide 10: Sample 2
Estimation: Function Point Analysis
FPA is composed of:
  Function Points
  Core Weightages
  Unadjusted Function Points
  General System Characteristics
  Value Adjustment Factor

## Slide 11: Sample 2
Estimation: Function Point Analysis
Function Points:
  External Input (EI): processes that handle data that comes from an outside source (e.g. Registration form, Add to cart).
  External Output (EO): processes that handle data sent outside to an external target (e.g. Registration confirmation message, Invoice).
  External Inquiries (EQ): processes that handle input-output combinations (e.g. Search for item’s stock and Send OK/Fail message).
  Internal Logical File (ILF): processes related to data maintained internally (e.g. database, files).
  External Interface File (EIF): processes related to data that is being maintained by another system integrated with our system (payment gateway, courier service).

## Slide 12: Sample 2
Estimation: Function Point Analysis
Core Weightages with respect to level of Complexity.
Weightages are predetermined and kept same for every function.
Measurement Parameter | Low | Average | High
Number of external inputs (EI) | 1 | 4 | 6
Number of external outputs (EO) | 1 | 5 | 7
Number of external inquiries (EQ) | 1 | 4 | 6
Number of internal files (ILF) | 1 | 10 | 15
Number of External Interfaces (EIF) | 1 | 7 | 10

## Slide 13: Sample 2
Estimation: Function Point Analysis
Unadjusted Function Points table counts all applicable FP parameters and calculates their weighted products.
Measurement Parameter | Count | Complexity | Weight | Total
Number of external inputs (EI) | 2 | Low | 3 | 6
Number of external outputs (EO) | … | … | … | …
Number of external inquiries (EQ) | … | … | … | …
Number of internal files (ILF) | … | … | … | …
Number of External Interfaces (EIF) | … | … | … | …

## Slide 14: Sample 2
Estimation: Function Point Analysis
General System Characteristics: we assign a number from 0 - 5 to each characteristic depending on its influence on the system.
Data Communications
Distributed Data Processing
Performance
Heavily Used Configuration
Transaction Rate
On-Line Data Entry
End-User Efficiency
On-Line Update
Complex Processing
ReusabiIity
Ease of Installation
Ease of Operation
Multiple Sites
Facilitate Change
Notes: If none of these factors influence the system, the sum would be 0. If all influence to maximum level, the sum would be 14x5=70

## Slide 15: Sample 2
Estimation: Function Point Analysis
Value Adjustment Factor (VAF) are two constants which come from the original calibration of Function Point Analysis by Allan Albrecht at IBM.
These values are 0.65 and 0.01
The first value is a baseline constant, telling us that even if all GSCs are zero, the system will still have some complexity.
Second value is a scaling factor that tells how important the GSC is in the Function Point Analysis.
Thus,

## Slide 16: Sample 2
Estimation: Function Point Analysis
Putting all in one place, the formula for FP Analysis is:
The Unadjusted Function Points come from UFP table, which is calculated with the help of FP Weightages.
is the sum of all 14 GSCs.
The role of VAF is to adjust complexity:
  Simplest project: ; FP will be 65% of UFP
  Highly complex project: ; FP will be 135% of UFP

## Slide 17: Sample 2
Estimation: Function Point Analysis – PakWheels
Identify FP Components
  EI (8): Vendor Registration, Customer Registration, Login, Add Product, Update Cart, Make Payment, Update Shipping detail, Input Validations
  EO (4): Order confirmation Email notification, Shipment tracking information, Admin reports, Error and validation messages.
  EQ (5): Browsing, Filtering, Search, View Cart, View Order History
  ILF (5): Users (customers, vendors, admin), Products, Orders, Order items, Inventory
  EIF (4): Leopard Courier API, Email service, SMS gateway, Payment gateway

## Slide 18: Sample 2
Estimation: Function Point Analysis – PakWheels
Core Weightages with respect to level of Complexity.
Weightages are predetermined and kept same for every function.
Measurement Parameter | Low | Average | High
Number of external inputs (EI) | 1 | 2 | 3
Number of external outputs (EO) | 2 | 3 | 5
Number of external inquiries (EQ) | 2 | 3 | 5
Number of internal files (ILF) | 3 | 5 | 8
Number of External Interfaces (EIF) | 5 | 8 | 13
Notes: Inputs are easy. So are external outputs and inquiries. The ILF is related to the database and raw files. External interfaces involve complex integrations, thus the high weightage.

## Slide 19: Sample 2
Estimation: Function Point Analysis – PakWheels
Unadjusted Function Points (as applicable)
We calculate the weighted sum
Measurement Parameter | Count | Complexity | Weight | Total
Number of external inputs (EI) | 8 | Low | 1 | 8
Number of external outputs (EO) | 4 | Average | 3 | 12
Number of external inquiries (EQ) | 5 | Average | 3 | 15
Number of internal files (ILF) | 5 | Low | 3 | 15
Number of External Interfaces (EIF) | 4 | High | 13 | 52
Notes: Total UFP = 102

## Slide 20: Sample 2
Estimation: Function Point Analysis – PakWheels
We only pick relevant General System Characteristics and score them.
Data Communications = 4
Performance = 2
Transaction Rate = 1
On-Line Data Entry = 4
End-User Efficiency = 3
On-Line Update = 5
Ease of Operation = 5
Facilitate Change = 3
GSC Sum = 27

## Slide 21: Sample 2
Estimation: Function Point Analysis – PakWheels
Calculation
93.5 FP means a medium-sized project that fits 1.4M budget and 4-month timeline.
1 FP ≈ 8 to 20 person-hours (depends on team), i.e. 2 developers working full time will complete in under 3 months.
There’s room. But 150+ means timeline will slip; 200+ means budget will break.
Notes: 0–50 FP → Small system. 50–200 FP → Medium system. 200+ FP → Large system

## Slide 22: Sample 2
Activity
Assuming another project which involves input through sensors and propagating the output to global Telecom hubs.
Measurement Parameter | Low | Average | High
Number of external inputs (EI) | 5 | 8 | 13
Number of external outputs (EO) | 3 | 5 | 8
Number of external inquiries (EQ) | 2 | 3 | 5
Number of internal files (ILF) | 3 | 5 | 8
Number of External Interfaces (EIF) | 8 | 13 | 21
Notes: Inputs are easy. So are external outputs and inquiries. The ILF is related to the database and raw files. External interfaces involve complex integrations, thus the high weightage.

## Slide 23: Sample 2
Activity
Calculate UFP
Measurement Parameter | Count | Complexity | Weight | Total
Number of external inputs (EI) |  |  |  | 
Number of external outputs (EO) |  |  |  | 
Number of external inquiries (EQ) |  |  |  | 
Number of internal files (ILF) |  |  |  | 
Number of External Interfaces (EIF) |  |  |  | 
Notes: Total UFP = 102

## Slide 24: Sample 2
Activity
Choose the ranking of General System Characteristics as applicable to calculate value of GSC.
Data Communications = ___
Distributed Data Processing = ___
Performance = ___
Heavily Used Configuration = ___
Transaction Rate = ___
On-Line Data Entry = ___
End-User Efficiency = ___
On-Line Update = ___
Complex Processing = ___
ReusabiIity = ___
Ease of Installation = ___
Ease of Operation = ___
Multiple Sites = ___
Facilitate Change = ___

## Slide 25: Sample 2
Activity
Calculate the VAF
Calculate FP
What does the result tell you about this project?

## Slide 26: THANK YOU
Owais Hussain
+92 345-3174270
owais.hussain@kiet.edu.pk
https://www.researchgate.net/profile/Owais-Hussain-3