## Slide 1: Software Engineering
Dr. Owais Hussain

## Slide 2: Agenda
Risk Management
Reactive vs Proactive
Principles
Types of Risk
Risk Identification and Impact
RMMM and Risk Table
This Photo by Unknown Author is licensed under CC BY

## Slide 3: Sample 2
Risk Management
All projects are prone to risks:
  What can go wrong?
  What’s the likelihood?
  What will the damage be?
  What can we do about it?
Risk Management involves:
  Risk Identification  Analysis  Planning  Tracking  Control

## Slide 4: Sample 2
Reactive vs Proactive Risk Management
Reactive: team reacts when they occur
  Mitigation: plan for additional resources for fire fighting.
  Fix: resources are allocated after the damage is done.
  Crisis management: project is in jeopardy as teams are not ready to respond to failures.
Reactive approach leads to project failures especially when the scope and scale are broad
Proactive: formal risk analysis mechanism
  Mitigation: organizations look for the root causes of risk.
  Total Quality Management (TQM): ensures potential issues are identified and addressed proactively.
  Crisis management: examining risk beyond the software bounds and developing skills to manage risks.

## Slide 5: Sample 2
Principles
Maintain global perspective: view software risks as a business problem.
Forward-looking view: think about the risks that may arise in the future; create contingency plans.
Open communication: if someone states a potential risk, don’t discount it.
Integrate: risk consideration must be integrated into the software engineering process.
Emphasize a continuous process: the team must be vigilant throughout the software process, modifying identified risks as more information is known and adding new ones as better insight is achieved.
Shared product vision: if all stakeholders share the same vision of the software, risk identification and assessment will be more accurate.
Teamwork: the talents, skills and knowledge of all stakeholder should be pooled in for risk management.

## Slide 6: Sample 2
Types of Risk
Performance risk
  The degree of uncertainty that the product will meet its requirements and be fit for its intended use.
Cost risk
  The degree of uncertainty that the project budget will be maintained.
Support risk
  The degree of uncertainty that the resultant software will be easy to correct, adapt, and enhance.
Schedule risk
  The degree of uncertainty that the project schedule will be maintained and that the product will be delivered on time.

## Slide 7: Sample 2
Risk Identification and Impact
Product size: risks associated with the overall size of the software to be built.
Business impact: risks associated with management or marketplace constraints.
Client characteristics: risks associated with client sophistication and team’s ability to effectively communicate with them.
Process definition: risks associated with the degree to which the SE process has been defined and followed by the team.
Development environment: risks associated with availability and quality of tools used to build the product.
Technology being built: risks associated with the complexity and newness of the system being built.
Staff (size and experience): risks associated with overall technical experience of the software team.

## Slide 8: Sample 2
Risk Identification and Impact
Attributes that affect risk due to Product Size:
  Estimated size of the product in LOC or FP
  Estimated size of product in number of programs, files transactions
  Percentage deviation in size of product from average for previous products
  Size of database created or used by the product
  Number of users of the product
  Number of projected changes to the requirements for the product before delivery and after delivery
  Amount of reused software

## Slide 9: Sample 2
Risk Identification and Impact
Attributes that affect risk due to Business Impact:
  Affect of this product on company revenue
  Visibility of this product by senior management
  Reasonableness of delivery deadline
  Number of clients who will use this product
  Interoperability constraints
  Sophistication of end users
  Amount and quality of documentation that must be delivered to the client
  Governmental constraints
  Costs associated with late delivery
  Costs associated with a defective product

## Slide 10: Sample 2
Risk Identification and Impact
Attributes that affect risk due to Client:
  Have you worked with the client in the past?
  Does the client have a solid idea of requirements?
  Has the client agreed to spend time with you?
  Is the client willing to participate in reviews?
  Is the client technically sophisticated?
  Is the client willing to let your people do the job or will he be looking over your shoulder during technically detailed work?
  Does the client understand the software engineering process?
Notes: If the client is indeed sitting with you during technical world, it’s a good thing in today’s development era (post AI)

## Slide 11: Sample 2
Risk Identification and Impact
Attributes that affect risk due to Process Maturity:
  Have you established a common process framework?
  Is it followed by project teams?
  Do you have management support for software engineering
  Do you have a proactive approach to SQA?
  Do you conduct formal technical reviews?
  Are CASE tools used for analysis, design and testing?
  Are the tools integrated with one another?
  Have document formats been established?

## Slide 12: Sample 2
Risk Identification and Impact
Attributes that affect risk due to Technology being built:
  Is the technology new to your organization?
  Are new algorithms, I/O technology required?
  Is new or unproven hardware involved?
  Is a specialized user interface required?
  Is the application radically different?
  Are you using new software engineering methods?
  Are you using unconventional software development methods, such as Al-based approaches?
  Are there significant performance constraints?
  Is it clear that the functionality requested is doable?

## Slide 13: Sample 2
Risk Identification and Impact
Attributes that affect risk due to Staff:
  Are the best people available?
  Does staff have the right skills?
  Are enough people available?
  Are staff committed for entire duration?
  Will some people work part time?
  Do staff have the right expectations?
  Have staff received necessary training?
  Will turnover among staff be low?

## Slide 14: Sample 2
RMMM and Risk Table
RMMM stands for Risk:
  Mitigation: how to minimize the occurrence?
  Monitoring: what data to track that will tell if the risk is becoming more or less likely?
  Management: what is the contingency plan if the risk becomes real?
Risk projection (a.k.a. risk estimation) rates each risk in two ways:
  Likelihood or probability that the risk is real.
  Consequences associated with the risk, should it occur.

## Slide 15: Sample 2
RMMM and Risk Table
Risk Projection steps:
  Establish a scale that reflects likelihood of a risk.
  Define the consequences of the risk.
  Estimate the impact of the risk on the project and the product.
  Note the overall accuracy of risk projection to remove confusion.
Build a risk table and sort by probability and impact

## Slide 16: Sample 2
RMMM and Risk Table – PakWheels
Risk ID | Risk Description | Probability (P) | Impact (I) | Exposure () | Owner
R1 | Scope creep due to additional feature requests beyond MVP | 5 | 5 | 25 | Project Manager
R2 | Leopard Courier API integration delays or technical issues | 4 | 5 | 20 | Lead Software Engineer
R3 | Filtering logic become more complex than anticipated | 4 | 4 | 16 | Business Analyst
R4 | Security vulnerabilities such as SQL Injection, XSS, or unauthorized access | 3 | 5 | 15 | Lead Software Engineer
R5 | Insufficient testing leading to defects in checkout, inventory, or order processing | 3 | 5 | 15 | Lead Quality Assurance Engineer
Risk ID | Risk Description | Probability (P) | Impact (I) |  | Owner
R1 | Scope creep due to additional feature requests beyond MVP | 5 | 5 | 25 | Project Manager
R2 | Leopard Courier API integration delays or technical issues | 4 | 5 | 20 | Lead Software Engineer
R3 | Filtering logic become more complex than anticipated | 4 | 4 | 16 | Business Analyst
R4 | Security vulnerabilities such as SQL Injection, XSS, or unauthorized access | 3 | 5 | 15 | Lead Software Engineer
R5 | Insufficient testing leading to defects in checkout, inventory, or order processing | 3 | 5 | 15 | Lead Quality Assurance Engineer
Probability: 1 = Very Low, 5 = Very High
Impact: 1 = Negligible, 5 = Critical
Risk Exposure = Probability × Impact
Note! this table does not include solution, it only highlights risks

## Slide 17: Sample 2
RMMM and Risk Table – PakWheels
Risk ID | Mitigation | Monitoring | Management
R1 | Freeze requirements after approval | Track change requests | Defer non-MVP features to future releases
R2 | Early integration and API prototyping | Monitor API success/failure rates | Switch to manual shipment creation temporarily
R3 | Design and validate data model early | Review query performance and filtering defects | Simplify filtering hierarchy for MVP
Choose which risks to attack based on:
  Available time and budget
  Impact

## Slide 18: THANK YOU
Owais Hussain
+92 345-3174270
owais.hussain@kiet.edu.pk
https://www.researchgate.net/profile/Owais-Hussain-3